## Prepare - 21 Jan
Group member | Personal Email | Mobile
ChungNT | chungntgt00508@fpt.edu.vn | 01678214991
ThanhPD | thanhpdgc00489@fpt.edu.vn | 0989169232
ThanhLC | thanhlcgt00510@fpt.edu.vn | 0989979087
LinhTH | linhthgt00478@fpt.edu.vn | 01254215227
DungNT | dungntgc00583@fpt.edu.vn | 0986825716
ThangNH | thangnhgc00645@fpt.edu.vn | 0962981614
Group information
Scheduled daily scrum: | Monday 08:00 PM
Wednesday on class
Saturday 08:00 PM
Tools | Visual Studio 2013
.NET Framework
Git hub
Source Tree Client

## Prepare - 23 Jan
Sartuday, 23/1 | Done | Will Do | Issue
ChungNT | Setup Visual Studio 2013 | Recall about DB | Too busy on company stuff
ThanhPD | Setup Enviroment | Design DB Diagram
ThanhLC | Setup Visual Studio 2013 | Read CSS and javascript
LinhTH | - Translate Coursework into Vietnamese - Design draft database script | Try to write more db script
DungNT | -Setup environment -Learn MVC 5 | Reseach about DB
ThangNH
Next activities
Complete product backlog
Sprint Planning
Determine which version of DBMS that integrate with VS2013, MVC5, .NET Framework

## Prepare - 25 Jan
Monday, 25/1 | Done | Will Do | Issue
ChungNT | Recall about DB, in progress | -Recall about DB (cont) - Analyze product backlog
ThanhPD | Make a draft about DB Diagram | - Complete DB Diagram - Analyze product backlog
ThanhLC
LinhTH
DungNT | Practice on Bootstrap Framework | Read requirements more
ThangNH
Next activities
Complete product backlog
Sprint Planning
Determine which version of DBMS that integrate with VS2013, MVC5, .NET Framework

## Sprint 1 - 28 Jan
Wednesday, 28/1 | Done | Will Do | Issue
ChungNT | - Recall about DB (cont) - Analyze product backlog | Do product backlog
ThanhPD | - Read product backlog - Design ERD - Research reporting task - Support Git & Source Tree client - Share tool for design DB Diagram (Vertabelo) | Do product backlog
ThanhLC | - Research about CSS3 and HTML5 - Read requirement | Do product backlog | Source Tree Issue
LinhTH | Write DB script | Write DB script | Source Tree Issue
DungNT | -Read requirement - Read about MVC5, Bootstrap | Do product backlog | Source Tree Issue
ThangNH
Notices
In next daily meeting, when telling about Done, need more details, must visualize which you have learnt
Tool to draw burndown chart | Excel
Scrum Desk