## Test Log
No | Module | Test-case | Step | Data | Expected Result | Run log
1 | Authentication | Redirect to default page after login success. - Admin - CL - CM - DLT - PVC | 1) Enter into Username textfield 2) Enter into Password textfield 3) Click on Submit button | Admin: admin/admin CL: CLAccount/123456 CM: CMAccount/123456 DLT: ??? PVC: ??? | Default page is displayed for each privellges | DLT account and PVC account are not provided
2 | Authentication | Login failed | 1) Enter into Username textfield 2) Enter into Password textfield 3) Click on Submit button | Any invalid username/password account | Message is shown to prompt re-check entered info | Passed
3 | Authentication | Attempt to authorized page (all of page except login page) | Enter valid urls to browser | Provide later | Redirect to login page | Many page still not completed
4 | CMR | View list CMR belong to - CL - CM - DLT - PVC | Go to manage CMRs page | CL: CLAccount/123456 CM: CMAccount/123456 DLT: ??? PVC: ??? | All CMRs belong to authenticated user are displayed | Can't create CMR because can't take annual course for CL
5 | CMR | View CMR details belong to - CL - CM - DLT - PVC | 1) Go to manage CMRs page 2) Select a CMR | CL: CLAccount/123456 CM: CMAccount/123456 DLT: ??? PVC: ??? | Detail page is display along with correct data | Can't create CMR because can't take annual course for CL
6 | CMR | Verify capacity to submit a CMR of CL | 1) Login with CL account 2) Go to manage CMRs page 3) Select a CMR | CL: CLAccount/123456 | 1) SEND is disabled if selected CMR whose status = Pending or Rejected 2) SEND is disabled for other status | Can't create CMR because can't take annual course for CL
7 | CMR | Verify editing CMR of CL | 1) Login with CL account 2) Go to manage CMRs page 3) Select a CMR 4) Change information to update 5) Click to Update button 6) Verify CMR detail after done | CL: CLAccount/123456 | New data wiil be updated | Can't create CMR because can't take annual course for CL
8 | CMR | Verify adding CMR ability | 1) Login with CL account 2) Go to list annual course page 3) Find a annual course which don't have report yet 4) Click Report button in this row 5) Provide info of CMR 6) Click Add button 7) Go to list annual course 8) Go to CMR list 9) Go to details of that CMR and verify | CL: CLAccount/123456 | 1) Add button is disappeared for that annual course 2) Go to CMR management to see status of created CMR is pending | Can't create CMR because can't take annual course for CL
9 | CMR | Verify validation when create CMR | 1) Login with CL account 2) Go to manage CMRs page 3) Select annual course which don't has CMR yet 4) Provide info of CMR 5) Click Add button | CL: CLAccount/123456 Data: Provide later | Error label is displayed and also prevent action add | Can't create CMR because can't take annual course for CL
10 | CMR | Verify ACR term is changed to CMR | Go to below pages to check: 1) List CMR 2) CMR details 3) Create CMR form |  | ARC term is no longer existed | Can't create CMR because can't take annual course for CL
11 | UI | Verify page is responsive in - View list CMR - View list user - View list Annual Course | N/A |  | Table will reorganize to columns and rows | No responsive
12 | Users | Verify DELETE capacity of admin | 1) Login with Admin account 2) Go to User List 3) Verify visibility of "Delete" button | Admin: admin/admin | User "Admin" is impossible to delete | Delete button visibility
13 | Users | Verify confirmation before delete an user | 1) Login with Admin account 2) Go to User List 3) Try to delete an user | Admin: admin/admin | Confirmation box must be displayed before perform action | Confirmation box is not shown
14 | UI | Verify display a status instead of a table without records on: 1) View list of CMR 2) View list of Course 3) View list of Annual Course 4) View list of Users | N/A |  | A status must be displayed to warning user that there is no record. | Annual Course of CL | CMR of CL | List of user ain't tested because there is atleast a user is Admin | List of course ain't tested because not be implemented yet
15 | Course | View list of course | 1) Login with Admin account 2) Click on Courses | Admin: admin/admin | List of course is displayed | Click on hyperlink to enter, but not response

## Test Log (3 April)
No | Module | Test-case | Step | Data | Expected Result | Test Log
1 | Authentication | Redirect to default page after login success. - Admin - CL - CM - DLT - PVC | 1) Enter into Username textfield 2) Enter into Password textfield 3) Click on Submit button | Admin: admin/admin CL: CLAccount/123456 CM: CMAccount/123456 DLT: DLTccount/123456 PVC: PVCccount/123456 | Default page is displayed for each privellges | Passed
3 | Authentication | Attempt to authorized page (all of page except login page) | Enter valid urls to browser | Provide later | Redirect to login page | Many page still not completed
4 | CMR | View list CMR belong to - CL - CM - DLT - PVC | Go to manage CMRs page | CL: CLAccount/123456 CM: CMAccount/123456 DLT: ??? PVC: ??? | All CMRs belong to authenticated user are displayed | DLT & PVC roles can't see list of CMR: Folder: Retest_3_April/bug4_dlt_pvc
5 | CMR | View CMR details belong to - CL - CM - DLT - PVC | 1) Go to manage CMRs page 2) Select a CMR | CL: CLAccount/123456 CM: CMAccount/123456 DLT: ??? PVC: ??? | Detail page is display along with correct data | Because DLT & PVC roles can't see list of CMR, can't execute
6 | CMR | Verify capacity to submit a CMR of CL | 1) Login with CL account 2) Go to manage CMRs page 3) Select a CMR | CL: CLAccount/123456 | 1) SEND is disabled if selected CMR whose status = Pending or Rejected 2) SEND is disabled for other status | Passed
7 | CMR | Verify editing CMR of CL | 1) Login with CL account 2) Go to manage CMRs page 3) Select a CMR 4) Change information to update 5) Click to Update button 6) Verify CMR detail after done | CL: CLAccount/123456 | New data wiil be updated | Passed
8 | CMR | Verify adding CMR ability | 1) Login with CL account 2) Go to list annual course page 3) Find a annual course which don't have report yet 4) Click Report button in this row 5) Provide info of CMR 6) Click Add button 7) Go to list annual course 8) Go to CMR list 9) Go to details of that CMR and verify | CL: CLAccount/123456 | 1) Add button is disappeared for that annual course 2) Go to CMR management to see status of created CMR is pending | Passed
9 | CMR | Verify validation when create CMR | 1) Login with CL account 2) Go to manage CMRs page 3) Select annual course which don't has CMR yet 4) Provide info of CMR 5) Click Add button | CL: CLAccount/123456 Data: Provide later | Error label is displayed and also prevent action add | Currently, there is no validation
10 | CMR | Verify ACR term is changed to CMR | Go to below pages to check: 1) List CMR 2) CMR details 3) Create CMR form |  | ARC term is no longer existed | Passed
11 | UI | Verify page is responsive in - View list CMR - View list user - View list of Course - View list Annual Course | N/A |  | Table will reorganize to columns and rows | List of CMR in CL roles still not affected File: Retest_3_April/bug11_list_cmr_of_cl.png
12 | Users | Verify DELETE capacity of admin | 1) Login with Admin account 2) Go to User List 3) Verify visibility of "Delete" button | Admin: admin/admin | User "Admin" is impossible to delete | Passed
13 | Users | Verify confirmation before delete an user | 1) Login with Admin account 2) Go to User List 3) Try to delete an user | Admin: admin/admin | Confirmation box must be displayed before perform action | Passed
14 | UI | Verify display a status instead of a table without records on: 1) View list of CMR 2) View list of Course 3) View list of Annual Course 4) View list of Users | N/A |  | A status must be displayed to warning user that there is no record. | Still happens with List of CMR: File: Retest_3_April/bug14_cmr_list.png
15 | Course | View list of course | 1) Login with Admin account 2) Click on Courses | Admin: admin/admin | List of course is displayed | Passed
16 | CMR | Verify confirmation before delete an CMR | 1) Login with CL account 2) Go to CMR management page 3) Try to delete CMR whose status = Rejected | CL: CLAccount/123456 | Confirmation box must be displayed before perform action | No confirmation was displayed
17 | Users | Verify EDIT capacity of admin | 1) Login with Admin account 2) Go to User List 3) Verify visibility of "Edit" button | Admin: admin/admin | User "Admin" is impossible to edit | Admin is still editable File: Retest_3_April/bug17_edit_admin.png

## Test Log (13 April)
No | Module | Test-case | Step | Data | Expected Result | Test Log
1 | Authentication | Redirect to default page after login success. - Admin - CL - CM - DLT - PVC | 1) Enter into Username textfield 2) Enter into Password textfield 3) Click on Submit button | Admin: admin/admin CL: CLAccount/123456 CM: CMAccount/123456 DLT: DLTccount/123456 PVC: PVCccount/123456 | Default page is displayed for each privellges | Passed
3 | Authentication | Attempt to authorized page (all of page except login page) | Enter valid urls to browser | Provide later | Redirect to login page | Passed
4 | CMR | View list CMR belong to - CL - CM - DLT - PVC | Go to manage CMRs page | CL: CLAccount/123456 CM: CMAccount/123456 DLT: ??? PVC: ??? | All CMRs belong to authenticated user are displayed | Passed
5 | CMR | View CMR details belong to - CL - CM - DLT - PVC | 1) Go to manage CMRs page 2) Select a CMR | CL: CLAccount/123456 CM: CMAccount/123456 DLT: ??? PVC: ??? | Detail page is display along with correct data | Passed
6 | CMR | Verify capacity to submit a CMR of CL | 1) Login with CL account 2) Go to manage CMRs page 3) Select a CMR | CL: CLAccount/123456 | 1) SEND is disabled if selected CMR whose status = Pending or Rejected 2) SEND is disabled for other status | Passed
7 | CMR | Verify editing CMR of CL | 1) Login with CL account 2) Go to manage CMRs page 3) Select a CMR 4) Change information to update 5) Click to Update button 6) Verify CMR detail after done | CL: CLAccount/123456 | New data wiil be updated | Passed
8 | CMR | Verify adding CMR ability | 1) Login with CL account 2) Go to list annual course page 3) Find a annual course which don't have report yet 4) Click Report button in this row 5) Provide info of CMR 6) Click Add button 7) Go to list annual course 8) Go to CMR list 9) Go to details of that CMR and verify | CL: CLAccount/123456 | 1) Add button is disappeared for that annual course 2) Go to CMR management to see status of created CMR is pending | Passed
9 | CMR | Verify validation when create CMR | 1) Login with CL account 2) Go to manage CMRs page 3) Select annual course which don't has CMR yet 4) Provide info of CMR 5) Click Add button | CL: CLAccount/123456 Data: Provide later | Error label is displayed and also prevent action add | Passed
10 | CMR | Verify ACR term is changed to CMR | Go to below pages to check: 1) List CMR 2) CMR details 3) Create CMR form |  | ARC term is no longer existed | Passed
11 | UI | Verify page is responsive in - View list CMR - View list user - View list of Course - View list Annual Course | N/A |  | Table will reorganize to columns and rows | Passed
12 | Users | Verify DELETE capacity of admin | 1) Login with Admin account 2) Go to User List 3) Verify visibility of "Delete" button | Admin: admin/admin | User "Admin" is impossible to delete | Passed
13 | Users | Verify confirmation before delete an user | 1) Login with Admin account 2) Go to User List 3) Try to delete an user | Admin: admin/admin | Confirmation box must be displayed before perform action | Passed
14 | UI | Verify display a status instead of a table without records on: 1) View list of CMR 2) View list of Course 3) View list of Annual Course 4) View list of Users | N/A |  | A status must be displayed to warning user that there is no record. | Passed
15 | Course | View list of course | 1) Login with Admin account 2) Click on Courses | Admin: admin/admin | List of course is displayed | Passed
16 | CMR | Verify confirmation before delete an CMR | 1) Login with CL account 2) Go to CMR management page 3) Try to delete CMR whose status = Rejected | CL: CLAccount/123456 | Confirmation box must be displayed before perform action | Passed
17 | Users | Verify EDIT capacity of admin | 1) Login with Admin account 2) Go to User List 3) Verify visibility of "Edit" button | Admin: admin/admin | User "Admin" is impossible to edit | Passed