## Sheet1
Sartuday, 23/1 | Done | Will Do | Issue
ChungNT | Setup Visual Studio 2013 | Recall about DB | Too busy on company stuff
ThanhPD
ThanhLC | Setup Visual Studio 2013 | Read CSS and javascript
LinhTH | - Translate Coursework into Vietnamese - Design draft database script | Try to write more db script
DungNT | -Setup environment -Learn MVC 5 | Reseach about DB
ThangNH
Next activities
Complete product backlog
Sprint Planning
Determine which version of DBMS that integrate with VS2013, MVC5, .NET Framework