## Sheet1
Monday, 25/1 | Done | Will Do | Issue
ChungNT | Recall about DB, in progress | -Recall about DB (cont) - Analyze product backlog
ThanhPD | Design DB diagram | - Analyze product backlog - Study about report
ThanhLC | Watch tutorials on CSS3, HTML5 | Continue on watching tutorials
LinhTH
DungNT | Practice on Bootstrap Framework | Read requirements more
ThangNH
Next activities
Complete product backlog
Sprint Planning
Determine which version of DBMS that integrate with VS2013, MVC5, .NET Framework