## Prepare - 21 Jan
Group member | Personal Email | Mobile
ChungNT | chungntgt00508@fpt.edu.vn | 01678214991
ThanhPD | thanhpdgc00489@fpt.edu.vn | 0989169232
ThanhLC | thanhlcgt00510@fpt.edu.vn | 0989979087
LinhTH | linhthgt00478@fpt.edu.vn | 01254215227
DungNT | dungntgc00583@fpt.edu.vn | 0986825716
ThangNH | thangnhgc00645@fpt.edu.vn | 0962981614
Group information
Scheduled daily scrum: | Monday 08:00 PM
Wednesday on class
Saturday 08:00 PM
Tools | Visual Studio 2013
.NET Framework
Git hub
Source Tree Client

## Prepare - 23 Jan
Sartuday, 23/1 | Done | Will Do | Issue
ChungNT | Setup Visual Studio 2013 | Recall about DB | Too busy on company stuff
ThanhPD | Setup Enviroment | Design DB Diagram
ThanhLC | Setup Visual Studio 2013 | Read CSS and javascript
LinhTH | - Translate Coursework into Vietnamese - Design draft database script | Try to write more db script
DungNT | -Setup environment -Learn MVC 5 | Reseach about DB
ThangNH
Next activities
Complete product backlog
Sprint Planning
Determine which version of DBMS that integrate with VS2013, MVC5, .NET Framework

## Prepare - 25 Jan
Monday, 25/1 | Done | Will Do | Issue
ChungNT | Recall about DB, in progress | -Recall about DB (cont) - Analyze product backlog
ThanhPD | Make a draft about DB Diagram | - Complete DB Diagram - Analyze product backlog
ThanhLC
LinhTH
DungNT | Practice on Bootstrap Framework | Read requirements more
ThangNH
Next activities
Complete product backlog
Sprint Planning
Determine which version of DBMS that integrate with VS2013, MVC5, .NET Framework

## Sprint 1 - 28 Jan
Wednesday, 28/1 | Done | Will Do | Issue
ChungNT | - Recall about DB (cont) - Analyze product backlog | Do product backlog
ThanhPD | - Read product backlog - Design ERD - Research reporting task - Support Git & Source Tree client - Share tool for design DB Diagram (Vertabelo) | Do product backlog
ThanhLC | - Research about CSS3 and HTML5 - Read requirement | Do product backlog | Source Tree Issue
LinhTH | Write DB script | Write DB script | Source Tree Issue
DungNT | -Read requirement - Read about MVC5, Bootstrap | Do product backlog | Source Tree Issue
ThangNH
Notices
In next daily meeting, when telling about Done, need more details, must visualize which you have learnt
Tool to draw burndown chart | Excel
Scrum Desk

## Sprint 1 - 30 Jan
Saturday, 30/1 | Done | Will Do | Issue
ChungNT | - Write guideline how to integrate Git with Eclipse - Draw draft ERD - Install Microsoft SQL 2012 | - DB design - Complete backlog - Plan for sprint 1
ThanhPD | - Read product backlog - Make more detail for task - Discuss to complete ERD - Get task on trello | - Research about chart in ASP.NET - Create demo ( line chart, circle chart)
ThanhLC | - Research bootstaps in dreamviewer - Research Responsive Web | - DB design - Complete backlog - Plan for sprint 1
LinhTH | Write DB script | - DB design - Complete backlog - Plan for sprint 1
DungNT | - Create simple demo about bootstap and MVC 5 | - DB design - Complete backlog - Plan for sprint 1
ThangNH
Notes after 31/1
Completed product backlog
Planned sprint 1
Using Microsoft Visual Studio 2012
Try to contact ThangNH
4/5 people started doing task
Retrospective
Meeting time should be 10:00 PM

## Sprint 2 - 15 Feb
Monday, 15/2 | Done | Will Do | Issue
ChungNT | - Create base project | - Sprint Planning
ThanhPD | - Research about chart in ASP.NET | - Create demo ( line chart, circle chart)
ThanhLC
LinhTH
DungNT | - Created login demo | - Manage staff
ThangNH

## Sprint 2 - 17 Feb
Wednesday, 17/2 | Done | Will Do | Issue
ChungNT | Update sql script | - Find way to write burndown chart - Prepare member's assessment
ThanhPD | Write demo of reporting function
ThanhLC | Design UI login
LinhTH | Write sql script
DungNT | Manage staff
ThangNH

## Sprint 2 - 20 Feb
Saturday, 20/2 | Done | Will Do | Issue
ChungNT |  | - Find way to write burndown chart - Prepare member's assessment - Create ACR
ThanhPD | - Code demo about chart | Send Email function
ThanhLC
LinhTH | Practice MVC | Practice MVC | Computer issue
DungNT |  | CL manage his own ACR
ThangNH

## Sprint 2 - 22 Feb
Monday, 22/2 | Done | Will Do | Issue
ChungNT | - Find way to write burndown chart - Prepare member's assessment - Create ACR (In progress) | Create ACR | Entity Framework issue
ThanhPD | - Study about send email function | - Implement send email function
ThanhLC |  | Comment
LinhTH | Practice MVC | Practice MVC | Computer issue
DungNT | CL manage his own ACR (In Progress) | CL manage his own ACR
ThangNH |  | Practice MVC
Retrospective
Warn to others for long-leave
Everyone must be kept in touch with rules in Scrum

## Sprint 3 - 25 Feb
Wednesday, 25/2 | Done | Will Do | Issue
ChungNT | Create ACR | - Update burn down chart - GitHub action - Review (Extract method)
ThanhPD | - Generate PDF - Email function | - Intergrate to base project | Base project problem
ThanhLC |  | - Take a task for Trello
LinhTH | - Setup Visual Studio | - Take a task for Trello
DungNT | - Complete Manage ACR | - Take a task for Trello
ThangNH |  | - Take a task for Trello | Not well at MVC5
Change ACR into CMR
Install-Package iTextSharp
Change code check eidt cmr
Track version of SQL

## Sprint 3 - 27 Feb
Saturday, 27/2 | Done | Will Do | Issue
ChungNT | Research test case template (In Progress) | Research test case template
ThanhPD | Guide Source Tree (In Progress) | Guide Source Tree
ThanhLC
LinhTH
DungNT | Fix code for review
ThangNH

## Sprint 3 - 29 Feb
Monday, 29/2 | Done | Will Do | Issue
ChungNT | Test case for module Authentication | Run test on deployment
ThanhPD | Guide Source Tree | Integrate email function & report function to base project
ThanhLC
LinhTH
DungNT |  | CM can list all CMR
ThangNH
Retrospective
Warn to others for long-leave
A sprint should take 2 weeks instead 1 like before

## Sprint 4 - 2 March
Wednesday, 2/3 | Done | Will Do | Issue
ChungNT | Done testcase
ThanhPD | Done sourcetree document
ThanhLC
LinhTH | Doing some task but don't assign any |  | Bug
DungNT | Fix some bug in project
ThangNH

## Sprint 4 - 5 March
Saturday 5/3 | Done | Will Do | Issue
ChungNT
ThanhPD
ThanhLC
LinhTH
DungNT
ThangNH

## Sprint 4 - 7 March
Monday 7/3 | Done | Will Do | Issue
ChungNT |  | Research drawing Sequence Diagrams
ThanhPD | CL can submit CMR (15 remain) | CL can submit CMR
ThanhLC
LinhTH
DungNT | CM can list all CMR (20 remain) | CM can list all CMR
ThangNH

## Sprint 4 - 14 March
Monday 14/3 | Done | Will Do | Issue
ChungNT | Research Linux Example (In Progress) | Follow Test Plan + Test Case template
ThanhPD | CL can submit CMR | Research meaningful course report information
ThanhLC
LinhTH | Admin can manage course | CL take Annual Course
DungNT |  | DLT/PVC can view CMR
ThangNH

## Sprint 4 - 9 March
Wednesday 9/3 | Done | Will Do | Issue
ChungNT | Research sequence diagram | - Write document about sequence diagram - Deploy and run test case
ThanhPD
ThanhLC
LinhTH | Manage course | Manage annual course
DungNT | CM can list all CMR
ThangNH

## Sprint 4 - 12 March
Saturday 12/3 | Done | Will Do | Issue
ChungNT | Research Linux Example (In Progress) | Research Linux Example
ThanhPD | CL can submit CMR (In Progress) | Research meaningful course report information
ThanhLC
LinhTH | Admin can manage course | CL take Annual Course
DungNT | Design responsive table | Create layout for main page of admin
ThangNH

## Sprint 5 - 16 March
Wednesday 16/3 | Done | Will Do | Issue
ChungNT |  | Test Plan + Test
ThanhPD | Research meaningful course report information | Integrate Report
ThanhLC |  | Commnet | Ko biet comment o dau
LinhTH | Admin can manage course | CL take Annual Course | SourceTree issue
DungNT |  | PVC,DLT
ThangNH

## Sprint 5 - 18 March
Saturday 18/3 | Done | Will Do | Issue
ChungNT
ThanhPD
ThanhLC
LinhTH | CL take Annual Course
DungNT | Edit create CMR page
ThangNH

## Sprint 5 - 21 March
Moday 21/3 | Done | Will Do | Issue
ChungNT | Test Plan + Test Log (Writing script to Sprint 3) | Continue writing test plan + test log
ThanhPD | View circle chart in CMR details page (In progress) | View circle chart in CMR details page
ThanhLC
LinhTH
DungNT
ThangNH

## Sprint 5 - 23 March
Wednesday 23/3 | Done | Will Do | Issue
ChungNT | Executed test plan to Sprint 3 | Continue writing and executing test plan
ThanhPD
ThanhLC | DLT can comment CMR (In progress) | DLT can comment CMR
LinhTH | 1) CL take annual course 2) View number of Active/Pending/Reported in course list 3) Course can be cancel | Merge current code to develop
DungNT | CM can approve CMR | Fix found bugs
ThangNH

## Sprint 5 - 26 March
Saturday 26/3 | Done | Will Do | Issue
ChungNT
ThanhPD
ThanhLC | Edit Logic of Delete Users
LinhTH | Insert 2 users of 2 role DLT & PVC
DungNT
ThangNH

## Sprint 5 - 28 March
Monday 28/3 | Done | Will Do | Issue
ChungNT
ThanhPD | View circle chart in CMR details page
ThanhLC
LinhTH | Commit latest code of Linh
DungNT
ThangNH

## Sprint 5 - 30 March
Wednesday 30/3 | Done | Will Do | Issue
ChungNT
ThanhPD
ThanhLC
LinhTH
DungNT | Table is not responsive
ThangNH

## Sprint 6 - 2 April
Saturday 2/4 | Done | Will Do | Issue
ChungNT | - Workaround to write mutual part in report | Execute test-plan
ThanhPD | Create summarize report (In progress) | Create summarize report | Database is in need to update to complete this task
ThanhLC | Edit display of table without records | Validate in comment | Aware conflictness when doing this task, commit later
LinhTH
DungNT | - DLT/PVC can view CMR - Put link into Email - Add status after response CMR - Put information into Email | Add some Security Method to project
ThangNH

## Sprint 6 - 4 April
Monday 4/4 | Done | Will Do | Issue
ChungNT | - Execute test plan | Write more test case
ThanhPD | Create summarize report (In progress) | Create summarize report
ThanhLC
LinhTH
DungNT |  | Fix found bugs
ThangNH

## Sprint 6 - 9 April
Monday 4/4 | Done | Will Do | Issue
ChungNT | Write script for DEMO (In progess)
ThanhPD | Report summarize (In progress)
ThanhLC
LinhTH | Write individual report
DungNT | Collect information to fill adding CMR form | Fix bugs
ThangNH

## Sprint 6 - 11 April
Monday 4/4 | Done | Will Do | Issue
ChungNT | Write script (in progess)
ThanhPD | Report summarize
ThanhLC
LinhTH | Write repot
DungNT | Tôi làm xong task collect data and fill CMR rồi
ThangNH