## Sprint 1
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Sprint 1 Backlog | 1) As the CL, I want to submit CMR |  |  |  |  | High | 3 | https://trello.com/c/l5ta2lze
Sprint 1 Backlog | 2) As the DLT, I can comment CMR |  |  |  |  | High | 1 | https://trello.com/c/3CoYtkHM
Sprint 1 Backlog | 4) As the member of system,I want to login in |  |  |  |  | Medium | 4 | https://trello.com/c/0QIMWZQO
Sprint 1 Backlog | 3) As the CM, I can approve CMR |  |  |  |  | High | 2 | https://trello.com/c/jDc23r3D
Sprint 1 - REVIEW | 4-1. Design GUI Login prototype. 8 |  |  |  | D |  | 9 | https://trello.com/c/2HDQD0hJ
Sprint 1 - REVIEW | 3-1. Code for generating report. 40 | [5 empty] | 7 | https://trello.com/c/2aPIIJcU
Sprint 1 - REVIEW | 0-2. Create database script. 5 | [5 empty] | 5 | https://trello.com/c/qAWDuo0U
Sprint 1 - REVIEW | 4-2. Code/Update GUI login and itself function. 8 |  |  |  | D |  | 8 | https://trello.com/c/5pR2bh3u
Sprint 1 - REVIEW | 0-1. Create project base. 40 | [5 empty] | 6 | https://trello.com/c/Bs5KaKbc

## Archived Sprint 1
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL