## Sprint 5
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Backlog | 1) As the DLT, I can comment CMR |  |  |  |  | High | 7 | https://trello.com/c/PHTXMVuW
Backlog | 3) As the CM, I can approve CMR |  |  |  |  | High | 10 | https://trello.com/c/scgPtnV7
Backlog | 7) As the CL, I want to submit CMR. |  |  |  |  | High | 11 | https://trello.com/c/BIw3F9HX
Backlog | 9) As the PVC, I can see CMR when it has been approved |  |  |  |  | Medium | 2 | https://trello.com/c/URmeUBcG
Backlog | 10) As the DLC, I can see CMR when it has been approved |  |  |  |  | Medium | 1 | https://trello.com/c/wpkOFzCU
Backlog | 11) As the guest of Faculty, I can view exception report |  |  |  |  | Medium | 12 | https://trello.com/c/dnOCDwDz
Backlog | 12) As the guest of Faculty, I can view statistical report |  |  |  |  | Medium | 4 | https://trello.com/c/xhN5RW1D
Backlog | 13) As the guest of Faculty, I can view approved CMR |  |  |  |  | Medium | 3 | https://trello.com/c/opqtYL0w
TODO | Create job to auto reject overdate report daily - 50 | [5 empty] | 18 | https://trello.com/c/DfkSVZwU
TODO | Edit display of table without records - 10 |  |  |  | TL |  | 24 | https://trello.com/c/cGp7xiEp
IN PROGRESS | 9, 10) DLT/PVC can view CMR - 30 |  |  |  | D | Added in Burndown | 14 | https://trello.com/c/HpiOZO7V
VERIFY | Edit create CMR page - 30 |  |  |  | D |  | 20 | https://trello.com/c/Kv0IU0As
VERIFY | 7) CL take Annual Course - 30 |  |  |  | TL | Added in Burndown | 17 | https://trello.com/c/0Sq7VDRt
VERIFY | Course can be cancel - 20 |  |  |  | TL |  | 27 | https://trello.com/c/4sHicKXn
VERIFY | 1) DLT comment CMR - 50 |  |  |  | TL | Added in Burndown | 15 | https://trello.com/c/HWeyNE6Z
VERIFY | 3) CM can approve CMR - 10 |  |  |  | D | Added in Burndown | 16 | https://trello.com/c/2rkqDLeo
VERIFY | View number of Active/Pending/Reported in course list - 10 |  |  |  | TL |  | 26 | https://trello.com/c/8fTHKKjt
VERIFY | Insert 2 users of 2 role DLT & PVC - 10 |  |  |  | TL |  | 21 | https://trello.com/c/kEK9NAM2
VERIFY | Commit latest code of Linh - 15 |  |  |  | TL |  | 25 | https://trello.com/c/1pfFKT6q
VERIFY | Edit Logic of Delete Users - 10 |  |  |  | TL |  | 23 | https://trello.com/c/RQrA4YrQ
VERIFY | Table is not responsive - 20 |  |  |  | D |  | 22 | https://trello.com/c/H2yDDBiV
VERIFY | View circle chart in CMR details page - 120 - 40 |  |  |  | (T |  | 19 | https://trello.com/c/NvaIly4W

## Archived Sprint 5
List | Title | Description | Points | Due | Members | Labels | Card # | Card URL
Backlog | [archived] 2) As the CM, I can view my own CMR only. |  |  |  |  | Medium | 9 | https://trello.com/c/o4VT98wD
Backlog | [archived] 4) As the CL, I can view my own CMR only |  |  |  |  | Medium | 5 | https://trello.com/c/J3WJVJKR
Backlog | [archived] 5) As the DLT, I can view all CMR. |  |  |  |  | Medium | 6 | https://trello.com/c/MlqVUbb5
Backlog | [archived] 6) As the PVC, I can view all CMR. |  |  |  |  | Medium | 8 | https://trello.com/c/4JSflU7i
Backlog | [archived] 8) As the admin, I can manage course. |  |  |  |  | Low | 13 | https://trello.com/c/RlhZCMdo